## TIME MANAGEME Gantt Chart
TIME MANAGEMENT GANTT CHART
[ Predicting Automotive Vehicles Engines ]
TASK NAME | START DATE | END DATE | DURATION (days)
Planning | 2023-06-01 | 2023-06-03 | 3
Research Related Article | 2023-06-04 | 2023-06-07 | 4
Data Gathering | 2023-06-08 | 2023-06-13 | 6
Data Preprocessing | 2023-06-14 | 2023-06-17 | 4
Feature Engineering | 2023-06-18 | 2023-06-23 | 6
Model Selection | 2023-06-24 | 2023-06-30 | 7
Model Training | 2023-07-01 | 2023-07-07 | 7
Model Evaluation | 2023-07-08 | 2023-07-11 | 4
Model Optimization | 2023-07-12 | 2023-07-16 | 5
Model Testing | 2023-07-17 | 2023-07-21 | 5
Maintenance | 2023-07-17 | 2023-07-21 | 5
Report Documentation | 2023-07-08 | 2023-07-22 | 15
Prepare Presentation | 2023-07-23 | 2023-07-24 | 2
Presentation | 2023-07-25 | 2023-07-25 | 1
Report Submission | 2023-07-26 | 2023-07-26 | 1
MILESTONE 1:
13/6/2023
Planning & Preparation Phase
MILESTONE 2:
7/7/2023
Implementation
MILESTONE 3:
21/7/2023
Maintenance & Optimize
MILESTONE 4:
26/7/2023
Submission